International School

Capstone Project 1

CMU-SE 450

C1SE.32

Project Plan

Version 1.0

Date: September 15th, 2026

FLTS: A RAG-Based Learning Content Generation Platform for Flipped Learning

Submitted by

Nguyen, Truong Cong Trieu

Khoa, Tra Van Minh

Hung, Le The Khanh

Vuong, Dang Trung

Approved by

MSc Huy, Truong Dinh

Proposal Review Panel Representative:

Name					Signature				Date

Capstone Project 1- Mentor:

Name					Signature				Date

PROJECT INFORMATION

| Project acronym | FLTS – Flipped Learning Teaching System |  |  |
| --- | --- | --- | --- |
| Project Title | Teaching And Learning Support System Based On The Flipped-Learning Method |  |  |
| Start Date | 03 Sep 2026 | End Date | 05 Dec 2026 |
| Lead Institution | International School, Duy Tan University |  |  |
| Project Mentor | MSc Huy, Truong Dinh |  |  |
| Scrum master / Project Leader & contact details | Nguyen, Truong Cong Trieu Email: shellingofficical@gmail.com Tel: 0907857735 |  |  |
| Partner Organization | Duy Tan University |  |  |
| Project Web URL |  |  |  |
| Team members | Name | Email | Tel |
|  | Nguyen, Truong Cong Trieu | shellingofficical@gmail.com | 0907857735 |
|  | Khoa, Tra Van Minh | minhkhoa131103@gmail.com | 0702665686 |
|  | Hung, Le The Khanh | lethekhanhhung1808@gmail.com | 0855482883 |
|  | Vuong, Dang Trung | Dangtrungvuong2020@gmail.com | 0349474291 |

DOCUMENT APPROVALS

The following signatures are required for approval of this document.

| Nguyen, Truong Cong Trieu Student ID: 25201205268 Scrum Master | Signature | Date |
| --- | --- | --- |
| Khoa, Tra Van Minh Student ID: 29219054767 Team Member | Signature | Date |
| Hung, Le The Khanh Student ID: 29211143657 Team Member | Signature | Date |
| Vuong, Dang Trung Student ID: 29211150834 Team Member | Signature | Date |

# REVISION HISTORY

| Version | Date | Comments | Author |
| --- | --- | --- | --- |
| 1.0 | September 15th, 2026 | Finalize the Project Plan according to the FLTS scope, implementation schedule, Sprint, effort of 16 hours/person/week, and agreed budget. | Flipped-Learning Team |

TABLE OF CONTENT

1. Introduction	6

1.1. Purpose of Document	6

2. Product Overview	6

2.1. Product Definition	6

2.2. Users & Stakeholders	6

2.2.1. User Needs	7

2.2.2. User Problems	7

2.3. Related Products & Solutions	7

3. Project Overview	7

3.1. Project Goal	7

3.2. Project Purpose	8

3.3. Project Context	8

3.4. Project Deliverables	8

4. Planning	9

4.1. Product Request (Product Backlog)	9

4.2. Sprint Backlog	11

5. Project Schedule Overview	12

6. Development Process	12

7. Team Organization	13

7.1. Scrum Team Information	13

7.2. Roles and Responsibilities	13

7.3. Communication Methods	14

7.4. Communication and Reporting	14

8. Schedule	15

8.1. Detailed Schedule	15

9. Budget	22

9.1. Cost Per Person/Hour	22

9.2. Total Estimated Cost	22

10. Project Risks	22

11. Product Delivery	24

12. Individual Contributions	25

1. Introduction

1.1. Purpose of Document

The Project Plan document defines how the FLTS team will organize, plan, execute, monitor, and complete the project during the period from September 3, 2026, to December 5, 2026. The document describes the objectives, product scope, work structure, Product Backlog at the planning level, Sprint Backlog at the overview level, timeline, development process, team organization, budget, risks, and deliverables.

The Project Plan serves as the project-level management document. Details of the User Story, Product Backlog, and Sprint Backlog will be managed in their respective documents/Excel spreadsheets and updated according to Scrum.

2. Product Overview

2.1. Product Definition

FLTS (Teaching and Learning Support System based on the Flipped-Learning Method) is a web-based system that helps instructors transform teaching materials into structured learning objects through a document-based AI pipeline. The system currently focuses on PDF and DOC/DOCX documents.

Learning objects within the product scope include quizzes, flashcards, mind maps, and interactive slides. The system employs a human-in-the-loop model: AI creates drafts; instructors preview, edit, request re-creation, approve, and publish; students only access published content.

The product includes key areas: authentication and authorization, course and document management, document processing and RAG, learning object generation, review and publication processes, student learning spaces, and basic learning analytics.

2.2. Users & Stakeholders

The system serves three main user groups:

- Lecturers: manage courses, upload materials, monitor processing, request the creation of Learning Objects, review/edit/regenerate, approve and publish content; view basic analytics.

- Students: access authorized courses and use published Learning Objects; take quizzes, view flashcards, mind maps, interactive slides, and record some learning events.

- Administrators: manage accounts and roles at a basic level, manage system data at the MVP level, and monitor basic operational status.

2.2.1. User Needs

- Instructors need to reduce the time spent converting teaching materials into learning activities while retaining control over content before publication.

- Students need a focused, user-friendly learning space that only displays content approved by instructors.

- Administrators need basic functionality to manage accounts, roles, and system status.

2.2.2. User Problems

- Creating quizzes, flashcards, mind maps, and slides from course materials can be time-consuming for instructors.

- AI-generated content may be inaccurate or irrelevant to the source material without a mechanism for verification and approval.

- Students need learning content that originates from course materials and is overseen by instructors.

- Project teams need to evaluate the quality of the RAG pipeline experimentally, rather than just assessing the system at the interface level.

2.3. Related Products & Solutions

Existing learning content creation platforms and AI tools demonstrate the ability to partially automate the creation of questions, flashcards, or presentation content. FLTS focuses on a more specific problem: creating Learning Objects from teaching materials, using document retrieval as the basis for content generation, and maintaining human-in-the-loop control so instructors can monitor the output before students use it.

3. Project Overview

3.1. Project Goal

The project aims to build and refine a web-based FLTS system capable of supporting the process from teaching materials to faculty-approved and published Learning Objects, and to build and evaluate a document-grounded RAG pipeline for research purposes.

The project will be implemented from 3/9/2026 to 05/12/2026, with a total planned effort of approximately 860 person-hours, equivalent to 4 members × 16 hours/week/person throughout the implementation period.

3.2. Project Purpose

The project aims to provide a tool to support instructors in preparing learning activities using the Flipped Learning method, helping to reduce the work of creating repetitive content, increase control over the quality of output, and provide students with learning objects organized according to the course.

3.3. Project Context

In the Flipped Learning model, students need access to learning materials and activities before or outside of class time. Preparing multiple types of learning content from the same document can add to the workload for instructors. FLTS is proposed to support the automation of the step of creating draft Learning Objects from documents, but it does not replace the professional decision-making of instructors.

Regarding the research, the project focuses on evaluating the RAG pipeline including document processing, chunking, embedding, retrieval, and generation. The research uses a dataset, ground truth, baseline, proposed method, evaluation metrics, and ablation study to verify quality.

3.4. Project Deliverables

Table 1. List of Project Deliverables

| No. | Deliverable | Description |
| --- | --- | --- |
| 1 | FLTS Web Application | Interface and functionality for Lecturers, Students, and Administrators within the MVP scope. |
| 2 | AI/RAG Service | Document processing, retrieval, and Learning Object generation services implemented via pipeline. |
| 3 | Database system | MySQL-based storage for accounts, courses, documents, Learning Objects, learning events, and related data. |
| 4 | Research Evaluation Package | Dataset, Ground Truth, Baseline, Proposed Method, metrics, experiment logs, and evaluation results. |
| 5 | Project documents | Project Plan, Requirements Engineering, Architecture, Test Plan/Test Cases/Test Report, and Technical Report as required by the course. |

4. Planning

4.1. Product Request (Product Backlog)

| PB ID | US ID | Feature | Actor | Priority | Sprint | Estimate |
| --- | --- | --- | --- | --- | --- | --- |
| PB01 | US-01 | Repository & Branching | Developer | High | Sprint 1 | 8h |
| PB02 | US-02 | Development Environment | Developer | High | Sprint 1 | 10h |
| PB03 | US-03 | Coding & Quality Standards | Developer | Medium | Sprint 1 | 6h |
| PB04 | US-04 | CI & Test Foundation | Developer | Medium | Sprint 1 | 8h |
| PB05 | US-05 | Registration | Lecturer / Student / Administrator | High | Sprint 1 | 12h |
| PB06 | US-06 | Login & Logout | User | High | Sprint 1 | 12h |
| PB07 | US-07 | Password Recovery | User | Medium | Sprint 1 | 8h |
| PB08 | US-08 | Role-Based Access Control | Administrator | High | Sprint 1 | 12h |
| PB09 | US-09 | Account & Role Management | Administrator | Medium | Sprint 1 | 10h |
| PB10 | US-10 | Course Management | Lecturer | High | Sprint 1 | 14h |
| PB11 | US-11 | Course Access Control | Lecturer / Student | High | Sprint 1 | 10h |
| PB12 | US-12 | Document Upload | Lecturer | High | Sprint 1 | 12h |
| PB13 | US-13 | Document Metadata & Status | Lecturer | High | Sprint 1 | 8h |
| PB14 | US-14 | Document Management | Lecturer | Medium | Sprint 1 | 8h |
| PB15 | US-15 | PDF Text Extraction | Lecturer | High | Sprint 2 | 16h |
| PB16 | US-16 | DOC/DOCX Text Extraction | Lecturer | High | Sprint 2 | 12h |
| PB17 | US-17 | Text Cleaning | Lecturer | Medium | Sprint 2 | 8h |
| PB18 | US-18 | Chunking | Lecturer | High | Sprint 2 | 12h |
| PB19 | US-19 | Embedding Generation | System | High | Sprint 2 | 14h |
| PB20 | US-20 | Vector Storage | System | High | Sprint 2 | 12h |
| PB21 | US-21 | Similarity Retrieval | System | High | Sprint 2 | 18h |
| PB22 | US-22 | Re-ranking & Context Optimization | System | Medium | Sprint 2 | 12h |
| PB23 | US-23 | RAG Generation Pipeline | System | High | Sprint 2 | 18h |
| PB24 | US-24 | Quiz Generation | Lecturer | High | Sprint 3 | 22h |
| PB25 | US-25 | Flashcard Generation | Lecturer | High | Sprint 3 | 18h |
| PB26 | US-26 | Mindmap Generation | Lecturer | High | Sprint 4 | 20h |
| PB27 | US-27 | Interactive Slide Generation | Lecturer | High | Sprint 4 | 22h |
| PB28 | US-28 | Structured Output Validation | System | High | Sprint 3 | 10h |
| PB29 | US-29 | Generation Parameters | Lecturer | Medium | Sprint 3 | 8h |
| PB30 | US-30 | Learning Object Preview | Lecturer | High | Sprint 3 | 12h |
| PB31 | US-31 | Learning Object Edit | Lecturer | High | Sprint 3 | 12h |
| PB32 | US-32 | Learning Object Regeneration | Lecturer | High | Sprint 3 | 10h |
| PB33 | US-33 | Approve & Publish | Lecturer | High | Sprint 3 | 14h |
| PB34 | US-34 | Learning Object Version & Status | Lecturer | Medium | Sprint 3 | 8h |
| PB35 | US-35 | Student Course Workspace | Student | High | Sprint 3 | 10h |
| PB36 | US-36 | Quiz Interaction | Student | High | Sprint 3 | 16h |
| PB37 | US-37 | Flashcard, Mindmap & Slide Interaction | Student | High | Sprint 4 | 12h |
| PB38 | US-38 | Learning Event Tracking | System | Medium | Sprint 4 | 10h |
| PB39 | US-39 | Basic Learning Analytics | Lecturer | Medium | Sprint 4 | 14h |
| PB40 | US-40 | Dataset & Ground Truth | Researcher | High | Sprint 4 | 12h |
| PB41 | US-41 | Baseline & Proposed Evaluation | Researcher | High | Sprint 4 | 16h |
| PB42 | US-42 | Ablation & Reproducibility | Researcher | High | Sprint 4 | 6h |

4.2. Sprint Backlog

Table 2. Sprint Backlog Table

| No. | Phase | User Story | Start Day | End Day |
| --- | --- | --- | --- | --- |
| 1 | SPR1 – Foundation | User Stories from EP01–EP03 | 25/09/2026 | 08/10/2026 |
| 2 | SPR2 – RAG Vertical Slice | User Stories from EP03–EP05 and the beginning of EP09 | 09/10/2026 | 22/10/2026 |
| 3 | SPR3 – MVP Learning Workflow | User Stories from EP05–EP07 | 23/10/2026 | 05/11/2026 |
| 4 | SPR4 – Completion & Research | Remaining User Stories from EP05, EP08–EP09 | 06/11/2026 | 19/11/2026 |

5. Project Schedule Overview

The project consists of 4 main development sprints, each lasting 2 weeks. These are preceded by the Start-up & Requirements phase; followed by Sprint 4 for QA & Stabilization and Final Release.

Table 3. Project Schedule Table

| No | Milestone | Start Time | Finish Time | Deliverables |
| --- | --- | --- | --- | --- |
| 1 | Start-up & Requirements | 03/09/2026 | 24/09/2026 | Project Plan, Requirements, Use Cases, Architecture, DB/API, UI/Test Strategy |
| 2 | Sprint 1 – Foundation | 25/09/2026 | 08/10/2026 | Authentication, RBAC, Course Management, Document Upload Foundation |
| 5 | Midterm report | 27/10/2026 | 30/10/2026 | Midterm Report and Proof of Progress |
| 3 | Sprint 2 – RAG Vertical Slice | 09/10/2026 | 22/10/2026 | Document Processing, Chunking, Embedding, Retrieval, RAG Prototype |
| 4 | Sprint 3 – MVP Learning Workflow | 23/10/2026 | 05/11/2026 | Quiz, Flashcard, Lecturer Review/Publish, Student Workspace |
| 6 | Sprint 4 – Completion & Research | 06/11/2026 | 19/11/2026 | Mindmap, Interactive Slide, Analytics, Dataset, Ground Truth, Baseline/Proposed Evaluation |
| 7 | QA & Stabilization | 20/11/2026 | 29/11/2026 | System Test, AI Quality Test, Regression, Bug Fixing, Deployment Verification |
| 8 | Final Release | 30/11/2026 | 05/12/2026 | Final Validation, Research Results, Documentation, Demo, Submission |

6. Development Process

The team applies Scrum in software development. Each Sprint has Sprint Planning, Sprint Execution, Daily Scrum, Sprint Review, and Sprint Retrospective. Work within a Sprint includes necessary design, coding, integration, testing, code review, and bug fixing.

- Sprint Planning: defines the Sprint Goal, selects Product Backlog Items, and breaks them down into tasks with estimated effort.

- Daily Scrum: updates progress, identifies obstacles, and adjusts tasks as needed.

- Sprint Execution: develops functionality, integrates components, writes tests, and reviews code.

- Sprint Review: presents completed increments and records feedback.

- Sprint Retrospective: evaluates the work and identifies improvements for the next Sprint.

For the research phase, the team follows a loop: prepares dataset/ground truth, builds baseline, develops proposed methods, runs evaluations, analyzes results, and re-tests using ablation/re-run. Research activities are distributed from Sprint 2 to Final Release, not entirely concentrated in Sprint 4.

7. Team Organization

7.1. Scrum Team Information

Table 4. Team Information Table

| Full Name | Phone | Email | Position |
| --- | --- | --- | --- |
| Trương Công Triều Nguyên | shellingofficical@gmail.com | 0907857735 | Scrum Master & Developer |
| Trà Văn Minh Khoa | minhkhoa131103@gmail.com | 0702665686 | Developer |
| Lê Thế Khánh Hưng | lethekhanhhung1808@gmail.com | 0855482883 | Developer |
| Đặng Trung Vương | Dangtrungvuong2020@gmail.com | 0349474291 | Developer |

7.2. Roles and Responsibilities

Table 5. Roles and Responsibilities Table

| Role | Responsibility Describe shortly each role | Name/Title |
| --- | --- | --- |
| Product Owner | Product orientation, prioritizing and defining the scope/value of the Product Backlog. | The representative/instructor will request the course/course guidance according to the established procedure. |
| Scrum Master | Coordinating Scrum events, supporting obstacle removal, monitoring progress and promoting process compliance. | Truong Cong Trieu Nguyen |
| Developer | Analyzing, designing, programming, integrating, testing, reviewing code and maintaining system quality. | All Members |
| Tester | Designing and implementing functional, integration, regression and AI quality testing; documenting and verifying defects. | All Members |

7.3. Communication Methods

Table 6. Communication Methods Table

| Audience/Attendees | Topic/Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| Mentor and Team Members | Project Progress Review | Weekly | Online meeting / Email |
| Team Members | Project Progress Review and Daily Meeting | Daily | Online meeting / Group chat |
| Scrum Team | Sprint Planning / Review / Retrospective | Per Sprint | Online / Face to face |

7.4. Communication and Reporting

Table 7. Communication and Reporting Table

| Type of communication | Methods, tools | Frequency | Information (Definition of the meeting) | People |
| --- | --- | --- | --- | --- |
| Communication among in group – Scrum meeting | Online meeting / Group chat | Daily | Progress, task updates, blockers, and daily plans | Project team |
| Sprint Planning Meeting | Online or Face to face | Once per Sprint | Define Sprint Goal and Sprint Backlog | Scrum Team |
| Retrospective meeting | Online or Face to face | Once per Sprint | Evaluate the process and suggest improvements | Scrum Team |
| Sprint review meeting, Demo | Online or Face to face | Once per Sprint | Demonstrate increments and gather feedback | Scrum Team |
| Bi-weekly status report | Project document / shared workspace | Bi-weekly | Summarize progress, results, issues, and next steps | Project team / Mentor |

8. Schedule

8.1. Detailed Schedule

Effort is estimated in person-hours. As required by the course, each member dedicates 16 hours per week to the project; with 4 members, the team capacity is 64 person-hours per week and 128 person-hours per 2-week Sprint. The total planned effort for the entire period is 860 person-hours, equivalent to 215 hours per person.

The Team capacity column maintains the structure of the Project Plan template and reflects the team's planned capacity/effort at higher-level work packages. Sub-tasks utilize detailed effort and are assigned to specific members.

Table 8. Detailed Schedule Table

| No. | Task Name | Effort | Start | Finish | Team capacity |
| --- | --- | --- | --- | --- | --- |
| 0 | Start-up & Requirements | 200h | 03/09/2026 | 24/09/2026 | 200h |
| 0.1 | Project Foundation | 30h | 03/09/2026 | 05/09/2026 |  |
| 0.1.1 | Kick-off meeting and agreement on working methods. | 4h | 03/09/2026 | 05/09/2026 |  |
| 0.1.2 | Set up the repository structure | 4h | 03/09/2026 | 05/09/2026 |  |
| 0.1.3 | Establish Git conventions and branches | 4h | 03/09/2026 | 05/09/2026 |  |
| 0.1.4 | Setting up Docker and development environment | 8h | 03/09/2026 | 05/09/2026 |  |
| 0.1.5 | Setting up frontend/backend/AI service environment | 6h | 03/09/2026 | 05/09/2026 |  |
| 0.1.6 | Setting up coding conventions and code review | 2h | 03/09/2026 | 05/09/2026 |  |
| 0.1.7 | Checking environment and repository | 2h | 03/09/2026 | 05/09/2026 |  |
| 0.2 | Requirements Engineering | 68h | 08/09/2026 | 15/09/2026 |  |
| 0.2.1 | Review Proposal and Scope | 8h | 08/09/2026 | 15/09/2026 |  |
| 0.2.2 | Functional Requirements Specification | 10h | 08/09/2026 | 15/09/2026 |  |
| 0.2.3 | Non-Functional Requirements Specification | 8h | 08/09/2026 | 15/09/2026 |  |
| 0.2.4 | Agent Analysis and Authorization | 8h | 08/09/2026 | 15/09/2026 |  |
| 0.2.5 | Define Use Cases | 8h | 08/09/2026 | 15/09/2026 |  |
| 0.2.6 | Use Case Specification | 10h | 08/09/2026 | 15/09/2026 |  |
| 0.2.7 | Building Acceptance Criteria | 6h | 08/09/2026 | 15/09/2026 |  |
| 0.2.8 | Review requirements | 10h | 08/09/2026 | 15/09/2026 |  |
| 0.3 | Architecture & Data Design | 70h | 16/09/2026 | 21/09/2026 |  |
| 0.3.1 | System architecture design | 10h | 16/09/2026 | 21/09/2026 |  |
| 0.3.2 | Container/component design | 8h | 16/09/2026 | 21/09/2026 |  |
| 0.3.3 | Database and ERD design | 10h | 16/09/2026 | 21/09/2026 |  |
| 0.3.4 | API contract design | 10h | 16/09/2026 | 21/09/2026 |  |
| 0.3.5 | AI service architecture design | 10h | 16/09/2026 | 21/09/2026 |  |
| 0.3.6 | RAG pipeline design | 8h | 16/09/2026 | 21/09/2026 |  |
| 0.3.7 | Security and authorization design | 6h | 16/09/2026 | 21/09/2026 |  |
| 0.3.8 | Architectural review | 8h | 16/09/2026 | 21/09/2026 |  |
| 0.4 | UI & Testing Foundation | 32h | 22/09/2026 | 24/09/2026 |  |
| 0.4.1 | Designing UI flow for Lecturers | 6h | 22/09/2026 | 24/09/2026 |  |
| 0.4.2 | Designing UI flow for Students | 6h | 22/09/2026 | 24/09/2026 |  |
| 0.4.3 | Designing UI flow for Administrators | 4h | 22/09/2026 | 24/09/2026 |  |
| 0.4.4 | Building test strategies | 6h | 22/09/2026 | 24/09/2026 |  |
| 0.4.5 | Building test case templates | 4h | 22/09/2026 | 24/09/2026 |  |
| 0.4.6 | Reviewing UI and test strategies | 6h | 22/09/2026 | 24/09/2026 |  |
| 1 | SPR1 – Foundation | 128h | 25/09/2026 | 08/10/2026 | 128h |
| 1.1.1 | Sprint Planning Meeting | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.1.2 | Building Sprint Backlog Sprint 1 | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.2.1 | Setting up Laravel structure and API foundation | 6h | 25/09/2026 | 08/10/2026 |  |
| 1.2.2 | Setting up migrations and database models | 6h | 25/09/2026 | 08/10/2026 |  |
| 1.2.3 | Normalizing API responses and error handling | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.2.4 | Setting up authentication API foundation | 6h | 25/09/2026 | 08/10/2026 |  |
| 1.3.1 | Implement Login API and Validation | 6h | 25/09/2026 | 08/10/2026 |  |
| 1.3.2 | Implement Registration API | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.3.3 | Implement password handling | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.3.4 | Implement Role model and migration | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.3.5 | Implement RBAC middleware | 6h | 25/09/2026 | 08/10/2026 |  |
| 1.3.6 | Test authentication and authorization | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.4.1 | Implement Vue routing | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.4.2 | Implement Login UI | 5h | 25/09/2026 | 08/10/2026 |  |
| 1.4.3 | Implement Registration UI | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.4.4 | Implement Authentication State Management | 5h | 25/09/2026 | 08/10/2026 |  |
| 1.4.5 | Implement Protected Routes | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.5.1 | Implement Course CRUD API | 8h | 25/09/2026 | 08/10/2026 |  |
| 1.5.2 | Implement Lecturer Course UI | 6h | 25/09/2026 | 08/10/2026 |  |
| 1.5.3 | Implement Course Authorization | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.5.4 | Course Integration Testing | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.6.1 | Implement PDF/DOC/DOCX upload API | 6h | 25/09/2026 | 08/10/2026 |  |
| 1.6.2 | Implement file validation | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.6.3 | Implement document metadata | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.6.4 | Implement upload UI | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.6.5 | Upload integration test | 4h | 25/09/2026 | 08/10/2026 |  |
| 1.7.1 | Sprint End Integration, Review, and Bug Fixing | 4h | 25/09/2026 | 08/10/2026 |  |
| 2 | SPR2 – RAG Vertical Slice | 128h | 09/10/2026 | 22/10/2026 | 128h |
| 2.1.1 | Sprint Planning Meeting | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.1.2 | Building the Sprint Backlog for Sprint 2 | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.2.1 | Implement PDF text extraction | 8h | 09/10/2026 | 22/10/2026 |  |
| 2.2.2 | Implement DOC/DOCX text extraction | 8h | 09/10/2026 | 22/10/2026 |  |
| 2.2.3 | Implement text normalization | 6h | 09/10/2026 | 22/10/2026 |  |
| 2.2.4 | Implement document processing API | 6h | 09/10/2026 | 22/10/2026 |  |
| 2.2.5 | Implement processing status | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.3.1 | Implement baseline chunking | 6h | 09/10/2026 | 22/10/2026 |  |
| 2.3.2 | Implement chunk metadata | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.3.3 | Prototype semantic chunking strategy | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.3.4 | Chunk quality testing | 6h | 09/10/2026 | 22/10/2026 |  |
| 2.4.1 | Integrate embedding service | 6h | 09/10/2026 | 22/10/2026 |  |
| 2.4.2 | Integrate vector store | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.4.3 | Implement document embedding pipeline | 6h | 09/10/2026 | 22/10/2026 |  |
| 2.4.4 | Implement vector metadata | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.4.5 | Vector storage testing | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.5.1 | Implement similarity retrieval | 6h | 09/10/2026 | 22/10/2026 |  |
| 2.5.2 | Implement top-k retrieval | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.5.3 | Implement retrieval API | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.5.4 | Retrieval result inspection | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.6.1 | Build RAG prompt template | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.6.2 | Implement context construction | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.6.3 | Integrate LLM generation | 6h | 09/10/2026 | 22/10/2026 |  |
| 2.6.4 | Validate structured JSON output | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.7.1 | Integrate document-to-RAG flow | 4h | 09/10/2026 | 22/10/2026 |  |
| 2.7.2 | Implement Quiz vertical slice prototype | 4h | 09/10/2026 | 22/10/2026 |  |
| 3 | SPR3 – MVP Learning Workflow | 128h | 23/10/2026 | 05/11/2026 | 128h |
| 3.1.1 | Sprint Planning Meeting | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.1.2 | Building the Sprint Backlog for Sprint 3 | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.2.1 | Designing the Quiz Schema | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.2.2 | Implement Quiz generation service | 6h | 23/10/2026 | 05/11/2026 |  |
| 3.2.3 | Implement question validation | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.2.4 | Implement Quiz preview | 6h | 23/10/2026 | 05/11/2026 |  |
| 3.2.5 | Quiz unit/integration testing | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.3.1 | Flashcard schema design | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.3.2 | Implement Flashcard generation | 6h | 23/10/2026 | 05/11/2026 |  |
| 3.3.3 | Implement Flashcard preview | 6h | 23/10/2026 | 05/11/2026 |  |
| 3.3.4 | Flashcard validation/testing | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.4.1 | Implement learning-object draft model | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.4.2 | Implement preview API | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.4.3 | Implement edit API | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.4.4 | Implement edit UI | 6h | 23/10/2026 | 05/11/2026 |  |
| 3.4.5 | Implement regenerate API | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.4.6 | Implement regenerate UI | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.5.1 | Implement approval workflow | 5h | 23/10/2026 | 05/11/2026 |  |
| 3.5.2 | Implement publication status | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.5.3 | Implement publish API | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.5.4 | Implement lecturer publish UI | 5h | 23/10/2026 | 05/11/2026 |  |
| 3.6.1 | Implement course learning page | 6h | 23/10/2026 | 05/11/2026 |  |
| 3.6.2 | Implement published-object access | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.6.3 | Implement Quiz player | 6h | 23/10/2026 | 05/11/2026 |  |
| 3.6.4 | Implement Flashcard player | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.6.5 | Student access testing | 4h | 23/10/2026 | 05/11/2026 |  |
| 3.7.1 | Integrate, fix bugs, and prepare a midterm demo. | 8h | 23/10/2026 | 05/11/2026 |  |
| 4 | SPR4 – Completion & Research | 128h | 06/11/2026 | 19/11/2026 | 128h |
| 4.1.1 | Sprint Planning meeting | 4h | 06/11/2026 | 19/11/2026 |  |
| 4.1.2 | Build the Sprint Backlog Sprint 4 | 4h | 06/11/2026 | 19/11/2026 |  |
| 4.2.1 | Design Mindmap schema | 4h | 06/11/2026 | 19/11/2026 |  |
| 4.2.2 | Implement Mindmap generation | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.2.3 | Implement Mindmap rendering | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.2.4 | Mindmap validation | 4h | 06/11/2026 | 19/11/2026 |  |
| 4.3.1 | Design Interactive Slide schema | 4h | 06/11/2026 | 19/11/2026 |  |
| 4.3.2 | Implement Slide generation | 2h | 06/11/2026 | 19/11/2026 |  |
| 4.3.3 | Implement Slide renderer | 8h | 06/11/2026 | 19/11/2026 |  |
| 4.3.4 | Implement slide navigation/interaction | 2h | 06/11/2026 | 19/11/2026 |  |
| 4.4.1 | Learning event model Design | 4h | 06/11/2026 | 19/11/2026 |  |
| 4.4.2 | Implement event recording API | 5h | 06/11/2026 | 19/11/2026 |  |
| 4.4.3 | Implement Quiz attempt recording | 4h | 06/11/2026 | 19/11/2026 |  |
| 4.4.4 | Implement basic lecturer analytics | 7h | 06/11/2026 | 19/11/2026 |  |
| 4.5.1 | Prepare the dataset | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.5.2 | Select and standardize documents | 4h | 06/11/2026 | 19/11/2026 |  |
| 4.5.3 | Establish the ground truth | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.5.4 | Annotation and validation | 8h | 06/11/2026 | 19/11/2026 |  |
| 4.6.1 | Implement baseline RAG | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.6.2 | Implement proposed RAG configuration | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.6.3 | Retrieval evaluation | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.6.4 | Generation evaluation | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.7.1 | Full learning-object integration | 6h | 06/11/2026 | 19/11/2026 |  |
| 4.7.2 | Research pipeline execution and bug fixing | 10h | 06/11/2026 | 19/11/2026 |  |
| 5 | QA & Stabilization | 92h | 20/11/2026 | 29/11/2026 | 92h |
| 5.1 | System-wide Functional Testing | 16h | 20/11/2026 | 29/11/2026 |  |
| 5.2 | Authentication and RBAC Testing | 8h | 20/11/2026 | 29/11/2026 |  |
| 5.3 | Document Processing Testing | 8h | 20/11/2026 | 29/11/2026 |  |
| 5.4 | Retrieval and RAG Testing | 10h | 20/11/2026 | 29/11/2026 |  |
| 5.5 | Learning Object Quality Testing | 10h | 20/11/2026 | 29/11/2026 |  |
| 5.6 | Student Learning Workflow Testing | 6h | 20/11/2026 | 29/11/2026 |  |
| 5.7 | API and Integration Testing | 8h | 20/11/2026 | 29/11/2026 |  |
| 5.8 | Regression Testing | 8h | 20/11/2026 | 29/11/2026 |  |
| 5.9 | Bug Fixing | 12h | 20/11/2026 | 29/11/2026 |  |
| 5.10 | Final QA Verification | 6h | 20/11/2026 | 29/11/2026 |  |
| 6 | Final Release | 56h | 30/11/2026 | 05/12/2026 | 56h |
| 6.1 | Production deployment | 8h | 30/11/2026 | 05/12/2026 |  |
| 6.2 | Deployment verification | 6h | 30/11/2026 | 05/12/2026 |  |
| 6.3 | Final database/data verification | 4h | 30/11/2026 | 05/12/2026 |  |
| 6.4 | Final system validation | 8h | 30/11/2026 | 05/12/2026 |  |
| 6.5 | Research result finalization | 8h | 30/11/2026 | 05/12/2026 |  |
| 6.6 | Technical documentation finalization | 6h | 30/11/2026 | 05/12/2026 |  |
| 6.7 | Final demo preparation | 6h | 30/11/2026 | 05/12/2026 |  |
| 6.8 | Code freeze and submission | 4h | 30/11/2026 | 05/12/2026 |  |
| 6.9 | Final backup/release package | 6h | 30/11/2026 | 05/12/2026 |  |

Total effort: Start-up & Requirements 200h + Sprint 1 128h + Sprint 2 128h + Sprint 3 128h + Sprint 4 128h + QA & Stabilization 92h + Final Release 56h = 860h.

9. Budget

9.1. Cost Per Person/Hour

Table 9. Cost Per Person/Hour

| Full Name | Role | Salary Rate (USD/hour) |
| --- | --- | --- |
| Trương Công Triều Nguyên | Scrum Master & Developer | 2 |
| Trà Văn Minh Khoa | Developer | 2 |
| Lê Thế Khánh Hưng | Developer | 2 |
| Đặng Trung Vương | Developer | 2 |

9.2. Total Estimated Cost

Table 10. Total Estimated Cost

| No. | Criteria | Price | Amount | Total (USD) |
| --- | --- | --- | --- | --- |
| 1 | Working hours | $2 / hour | 860 hours | 1,720 |
| 2 | Other project cost | $100 / member | 4 members | 400 |
|  | Total |  |  | 2,120 |

Explain:

- Total working hours = Total Effort = 860 person-hours.

- Cost of working hours = 860 × $2/hour = $1,720.

- Other project cost = 4 members × $100/member = $400.

- Total estimated project cost = $1,720 + $400 = $2,120.

10. Project Risks

The group used a Probability and Impact scale from 1 to 5. Risk Exposure = Probability × Impact. Higher scores indicate risks that require priority control.

Table 11. Project Risks

| Risk | Definition | Probability | Impact | Risk Exposure | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| Inaccurate effort estimates | The actual effort for some tasks may be higher than estimated, especially with RAG and AI integration. | 4 | 4 | 16 | Monitor actual effort; break down tasks into larger ones; review estimates in Sprint Planning; adjust Sprint Backlog as needed. |
| Changes or missing requirements | Unclear requirements or changes that affect scope and timeline | 3 | 4 | 12 | Define scope using proposals; manage change via product backlog; confirm acceptance criteria before development. |
| Technical difficulties with RAG/AI | The quality of retrieval or generation is unsatisfactory, or AI service integration is faulty. | 5 | 5 | 25 | Implement technical spikes early; build baselines beforehand; log experiments; test with datasets/ground truth; have fallback plans. |
| Unstable document format | PDF/DOC/DOCX files have different structures, causing extraction or chunking errors. | 4 | 4 | 16 | Clearly define supported formats; build diverse test data; validate processing status; handle errors and retry appropriately. |
| Uneven programming experience | Team members may encounter difficulties with new technologies or complex tasks. | 4 | 3 | 12 | Pair programming; code review; research spikes; break tasks into smaller parts and share knowledge in Daily Scrum. |
| Conflicts or lack of team coordination | Lack of communication or unbalanced assignment of tasks affects progress. | 3 | 3 | 9 | Daily Scrum, Sprint Retrospective, transparent tasks and workload; address blockers early. |
| Frontend/backend/AI integration error | Privately developed services may not match APIs or data contracts. | 4 | 4 | 16 | Finalize API contracts early; continuous integration testing; implement vertical slicing from Sprint 2. |

11. Product Delivery

Table 12. Product Delivery Table

| No. | Document | Deadline | File Name |
| --- | --- | --- | --- |
| 1 | Final Project Plan Document | 05/12/2026 | FLTS_Project_Plan_Tieng_Viet_v1.0.docx |
| 2 | Product Backlog & Sprint Backlog | According to the Sprint/Final plan | FLTS_Product_Backlog.xlsx / FLTS_Sprint_Backlog.xlsx |
| 3 | Source Code Repository | 05/12/2026 | Link GitHub/GitLab |
| 4 | Final Web Application | 05/12/2026 | Link Hosting/Deployment |
| 5 | System Specification / Architecture | According to the subject plan | System_Spec_v1.0.pdf |
| 6 | Test Plan, Test Cases & Test Report | 29/11/2026 | Test_Plan / Test_Cases / Test_Report |
| 7 | Research Evaluation Package | 05/12/2026 | Dataset, Ground Truth, Experiment Logs, Evaluation Results |
| 8 | Technical Report | 05/12/2026 | FLTS_Technical_Report.pdf |

12. Individual Contributions

According to the team's principles, all four members participated in coding, testing, integration, and a portion of the research work. With a total effort of 860 person-hours, the allocation plan was balanced at 215 hours per person throughout the entire implementation phase.

Table 13. Individual Contributions Table

| No. | Team member | Contribution in % |
| --- | --- | --- |
| 1 | Trương Công Triều Nguyên | 100% |
| 2 | Trà Văn Minh Khoa | 100% |
| 3 | Lê Thế Khánh Hưng | 100% |
| 4 | Đặng Trung Vương | 100% |

Effort allocation basis: Start-up & Requirements 50 hours/person; each Sprint 32 hours/person; QA & Stabilization 23 hours/person; Final Release 14 hours/person. Total 215 hours/person, equivalent to 16 hours/week/person according to the total planned duration.