## Estimate
Project Name: |  | FLTS - Teaching and Learning Support System
Module Name: |  | Sprint 1 - Foundation
Development Team: |  | FLTS Capstone Project Team
Start Date: |  | 2026-09-25
End Date: |  | 2026-10-08
On Time
No. | Member Name |  | Estimate |  |  |  | Lately
1 | Nguyen | Truong Cong Trieu Nguyen | 32 |  |  |  | Early
2 | Khoa | Tra Van Minh Khoa | 32 |  |  |  | Unfinished
3 | Hung | Le The Khanh Hung | 32
4 | Vuong | Dang Trung Vuong | 32
PB ID | Task Description |  | Responsible Member | Estimate | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08
SPR1 | Sprint Planning Meeting |  | All Members | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPR1 | Create Sprint 1 Backlog |  | All Members | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPR1 | Create Sprint 1 Test Plan |  | Vuong | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB01 | Initialize Git repository and project structure |  | Nguyen | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB01 | Define Git branching strategy |  | Nguyen | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB01 | Configure branch protection and pull request rules |  | Nguyen | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB02 | Create Docker Compose services |  | Khoa | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB02 | Configure Laravel backend environment |  | Khoa | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB02 | Configure Vue frontend environment |  | Hung | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB02 | Verify local development environments |  | Nguyen | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB03 | Define coding conventions |  | Nguyen | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB03 | Create code review checklist |  | Nguyen | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB04 | Configure CI pipeline |  | Khoa | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB04 | Create unit-test foundation |  | Vuong | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB04 | Configure linting and quality checks |  | Nguyen | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB05 | Implement Registration API |  | Khoa | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB05 | Build Registration UI |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB05 | Validate registration inputs and errors |  | Vuong | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB06 | Implement Login API |  | Khoa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB06 | Build Login UI |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB06 | Implement logout and session handling |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB07 | Implement password-reset token and API |  | Khoa | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
PB07 | Build password recovery UI and email flow |  | Hung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
PB07 | Test password recovery |  | Vuong | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
PB08 | Create role and permission schema |  | Khoa | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
PB08 | Implement RBAC middleware |  | Khoa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
PB08 | Test authorization rules |  | Vuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0
PB09 | Implement account list and detail API |  | Vuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0
PB09 | Implement role assignment and update |  | Nguyen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0
PB09 | Test account and role management |  | Vuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
PB10 | Implement Course CRUD API |  | Hung | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0 | 0 | 0
PB10 | Build Lecturer course management UI |  | Hung | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
PB10 | Test course management integration |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0
PB11 | Create course access and enrollment model |  | Khoa | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0
PB11 | Implement course access middleware |  | Vuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0
PB11 | Test Lecturer and Student access |  | Vuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
PB12 | Implement document upload API |  | Vuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
PB12 | Build document upload UI |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
PB12 | Validate file type, size, and upload errors |  | Vuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
PB13 | Create document metadata schema |  | Nguyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
PB13 | Implement processing status tracking |  | Nguyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
PB13 | Display metadata and processing status |  | Nguyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
PB14 | Implement document list and search |  | Nguyen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
PB14 | Implement download and delete actions |  | Nguyen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
PB14 | Test document management integration |  | Nguyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
SPR1 | Integrate Sprint 1 modules and resolve conflicts |  | All Members | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
SPR1 | Run regression tests and fix defects |  | All Members | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
SPR1 | Conduct Sprint Review and Retrospective |  | All Members | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
|  |  | TOTAL | 128 | 128 | 116 | 110 | 101 | 94 | 90 | 82 | 73 | 64 | 57 | 49 | 37 | 16 | 0

## Actual
Project Name: |  | FLTS - Teaching and Learning Support System
Module Name: |  | Sprint 1 - Foundation
Development Team: |  | FLTS Capstone Project Team
Start Date: |  | 2026-09-25
End Date: |  | 2026-10-08
On Time
No. | Member Name |  | Estimate | Actual |  |  | Lately
1 | Nguyen | Truong Cong Trieu Nguyen | 32 |  |  |  | Early
2 | Khoa | Tra Van Minh Khoa | 32 |  |  |  | Unfinished
3 | Hung | Le The Khanh Hung | 32
4 | Vuong | Dang Trung Vuong | 32
PB ID | Task Description |  | Responsible Member | Actual | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08
SPR1 | Sprint Planning Meeting |  | All Members
SPR1 | Create Sprint 1 Backlog |  | All Members
SPR1 | Create Sprint 1 Test Plan |  | Vuong
PB01 | Initialize Git repository and project structure |  | Nguyen
PB01 | Define Git branching strategy |  | Nguyen
PB01 | Configure branch protection and pull request rules |  | Nguyen
PB02 | Create Docker Compose services |  | Khoa
PB02 | Configure Laravel backend environment |  | Khoa
PB02 | Configure Vue frontend environment |  | Hung
PB02 | Verify local development environments |  | Nguyen
PB03 | Define coding conventions |  | Nguyen
PB03 | Create code review checklist |  | Nguyen
PB04 | Configure CI pipeline |  | Khoa
PB04 | Create unit-test foundation |  | Vuong
PB04 | Configure linting and quality checks |  | Nguyen
PB05 | Implement Registration API |  | Khoa
PB05 | Build Registration UI |  | Hung
PB05 | Validate registration inputs and errors |  | Vuong
PB06 | Implement Login API |  | Khoa
PB06 | Build Login UI |  | Hung
PB06 | Implement logout and session handling |  | Hung
PB07 | Implement password-reset token and API |  | Khoa
PB07 | Build password recovery UI and email flow |  | Hung
PB07 | Test password recovery |  | Vuong
PB08 | Create role and permission schema |  | Khoa
PB08 | Implement RBAC middleware |  | Khoa
PB08 | Test authorization rules |  | Vuong
PB09 | Implement account list and detail API |  | Vuong
PB09 | Implement role assignment and update |  | Nguyen
PB09 | Test account and role management |  | Vuong
PB10 | Implement Course CRUD API |  | Hung
PB10 | Build Lecturer course management UI |  | Hung
PB10 | Test course management integration |  | Hung
PB11 | Create course access and enrollment model |  | Khoa
PB11 | Implement course access middleware |  | Vuong
PB11 | Test Lecturer and Student access |  | Vuong
PB12 | Implement document upload API |  | Vuong
PB12 | Build document upload UI |  | Hung
PB12 | Validate file type, size, and upload errors |  | Vuong
PB13 | Create document metadata schema |  | Nguyen
PB13 | Implement processing status tracking |  | Nguyen
PB13 | Display metadata and processing status |  | Nguyen
PB14 | Implement document list and search |  | Nguyen
PB14 | Implement download and delete actions |  | Nguyen
PB14 | Test document management integration |  | Nguyen
SPR1 | Integrate Sprint 1 modules and resolve conflicts |  | All Members
SPR1 | Run regression tests and fix defects |  | All Members
SPR1 | Conduct Sprint Review and Retrospective |  | All Members
TOTAL

## Chart
Sprint 1 Capstone Progress Charts
Date | Planned Remaining | Actual Remaining | Ideal Remaining | Date | Planned Completed | Actual Completed | Total Scope
25-Sep | 128 |  | 128 | 25-Sep | 0 |  | 128
26-Sep | 116 |  | 118.1538 | 26-Sep | 12 |  | 128
27-Sep | 110 |  | 108.3077 | 27-Sep | 18 |  | 128
28-Sep | 101 |  | 98.4615 | 28-Sep | 27 |  | 128
29-Sep | 94 |  | 88.6154 | 29-Sep | 34 |  | 128
30-Sep | 90 |  | 78.7692 | 30-Sep | 38 |  | 128
01-Oct | 82 |  | 68.9231 | 01-Oct | 46 |  | 128
02-Oct | 73 |  | 59.0769 | 02-Oct | 55 |  | 128
03-Oct | 64 |  | 49.2308 | 03-Oct | 64 |  | 128
04-Oct | 57 |  | 39.3846 | 04-Oct | 71 |  | 128
05-Oct | 49 |  | 29.5385 | 05-Oct | 79 |  | 128
06-Oct | 37 |  | 19.6923 | 06-Oct | 91 |  | 128
07-Oct | 16 |  | 9.8462 | 07-Oct | 112 |  | 128
08-Oct | 0 |  | 0 | 08-Oct | 128 |  | 128