## Estimate
Project Name: |  | FLTS - Teaching and Learning Support System
Module Name: |  | Sprint 2 - RAG Vertical Slice
Development Team: |  | FLTS Capstone Project Team
Start Date: |  | 2026-10-09
End Date: |  | 2026-10-22
On Time
No. | Member Name |  | Estimate |  |  |  | Lately
1 | Nguyen | Truong Cong Trieu Nguyen | 32
2 | Khoa | Tra Van Minh Khoa | 32
3 | Hung | Le The Khanh Hung | 32
4 | Vuong | Dang Trung Vuong | 32
PB ID | Task Description |  | Responsible Member | Estimate | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22
SPR2 | Sprint Planning Meeting |  | All Members | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPR2 | Create Sprint 2 Backlog |  | All Members | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPR2 | Create / update Sprint 2 Test Plan |  | Vuong | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB04 | Fix CI PHP version and run GitHub Actions workflow |  | Khoa | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB13 | Design processing-run schema and document status state machine |  | Nguyen | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB13 | Implement Laravel trigger, queue job, retry and status API |  | Nguyen | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB13 | Display processing status and errors in Lecturer UI |  | Hung | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB15 | Implement text-based PDF extraction with page metadata |  | Khoa | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB15 | Test valid, empty and corrupt PDF handling |  | Vuong | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB15 | Implement PDF extraction error mapping and persistence |  | Khoa | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB16 | Implement DOCX extraction |  | Khoa | 5 | 5 | 5 | 5 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB16 | Implement legacy DOC conversion/extraction spike |  | Khoa | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB16 | Test DOC/DOCX fixtures and error cases |  | Vuong | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB17 | Implement text cleaning and normalization |  | Khoa | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB17 | Write cleaning/normalization unit tests |  | Vuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB18 | Define chunk configuration version and metadata schema |  | Nguyen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB18 | Implement baseline paragraph/sentence chunking |  | Khoa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB18 | Test chunk boundaries, overlap and source linkage |  | Vuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB18 | Display chunk summary in Lecturer UI |  | Hung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PB19 | Integrate local embedding model with ChromaDB |  | Vuong | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0
PB19 | Wire FastAPI embedding workflow and configuration |  | Khoa | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
PB19 | Handle embedding errors and record processing failure |  | Vuong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0
PB20 | Configure persistent ChromaDB collection/volume |  | Vuong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
PB20 | Add vector-reference migration and model linkage |  | Nguyen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
PB20 | Implement vector upsert/delete lifecycle |  | Khoa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
PB21 | Implement similarity search and Top-K result formatting |  | Vuong | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
PB21 | Implement authorized Laravel retrieval-test API |  | Nguyen | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
PB21 | Build Lecturer retrieval-test UI |  | Hung | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
PB21 | Integration test retrieval, course access and source metadata |  | Vuong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
PB23 | Build evidence-retrieval prototype UI with citations |  | Hung | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
PB23 | Create evidence-only RAG prototype endpoint |  | Nguyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
PB23 | Run demo evidence checks and document limitations |  | Vuong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
SPR2 | Integrate Sprint 2 modules and resolve conflicts |  | All Members | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
SPR2 | Run regression tests and fix defects |  | All Members | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
SPR2 | Conduct Sprint Review and Retrospective |  | All Members | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
TOTAL |  |  |  | 128 | 128 | 118 | 108 | 98 | 88 | 78 | 68 | 58 | 48 | 38 | 28 | 18 | 8 | 0

## Actual
Project Name: |  | FLTS - Teaching and Learning Support System
Module Name: |  | Sprint 2 - RAG Vertical Slice
Development Team: |  | FLTS Capstone Project Team
Start Date: |  | 2026-10-09
End Date: |  | 2026-10-22
On Time
No. | Member Name |  | Estimate | Actual |  |  | Lately
1 | Nguyen | Truong Cong Trieu Nguyen | 32
2 | Khoa | Tra Van Minh Khoa | 32
3 | Hung | Le The Khanh Hung | 32
4 | Vuong | Dang Trung Vuong | 32
PB ID | Task Description |  | Responsible Member | Actual | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22
SPR2 | Sprint Planning Meeting |  | All Members
SPR2 | Create Sprint 2 Backlog |  | All Members
SPR2 | Create / update Sprint 2 Test Plan |  | Vuong
PB04 | Fix CI PHP version and run GitHub Actions workflow |  | Khoa
PB13 | Design processing-run schema and document status state machine |  | Nguyen
PB13 | Implement Laravel trigger, queue job, retry and status API |  | Nguyen
PB13 | Display processing status and errors in Lecturer UI |  | Hung
PB15 | Implement text-based PDF extraction with page metadata |  | Khoa
PB15 | Test valid, empty and corrupt PDF handling |  | Vuong
PB15 | Implement PDF extraction error mapping and persistence |  | Khoa
PB16 | Implement DOCX extraction |  | Khoa
PB16 | Implement legacy DOC conversion/extraction spike |  | Khoa
PB16 | Test DOC/DOCX fixtures and error cases |  | Vuong
PB17 | Implement text cleaning and normalization |  | Khoa
PB17 | Write cleaning/normalization unit tests |  | Vuong
PB18 | Define chunk configuration version and metadata schema |  | Nguyen
PB18 | Implement baseline paragraph/sentence chunking |  | Khoa
PB18 | Test chunk boundaries, overlap and source linkage |  | Vuong
PB18 | Display chunk summary in Lecturer UI |  | Hung
PB19 | Integrate local embedding model with ChromaDB |  | Vuong
PB19 | Wire FastAPI embedding workflow and configuration |  | Khoa
PB19 | Handle embedding errors and record processing failure |  | Vuong
PB20 | Configure persistent ChromaDB collection/volume |  | Vuong
PB20 | Add vector-reference migration and model linkage |  | Nguyen
PB20 | Implement vector upsert/delete lifecycle |  | Khoa
PB21 | Implement similarity search and Top-K result formatting |  | Vuong
PB21 | Implement authorized Laravel retrieval-test API |  | Nguyen
PB21 | Build Lecturer retrieval-test UI |  | Hung
PB21 | Integration test retrieval, course access and source metadata |  | Vuong
PB23 | Build evidence-retrieval prototype UI with citations |  | Hung
PB23 | Create evidence-only RAG prototype endpoint |  | Nguyen
PB23 | Run demo evidence checks and document limitations |  | Vuong
SPR2 | Integrate Sprint 2 modules and resolve conflicts |  | All Members
SPR2 | Run regression tests and fix defects |  | All Members
SPR2 | Conduct Sprint Review and Retrospective |  | All Members
TOTAL

## Chart
Sprint 2 - RAG Vertical Slice: Burndown and Burnup Charts
Date | Planned Remaining | Actual Remaining | Ideal Remaining | Date | Planned Completed | Actual Completed | Total Scope
09-Oct | 128 |  | 128 | 09-Oct | 0 |  | 128
10-Oct | 118 |  | 118.1538 | 10-Oct | 10 |  | 128
11-Oct | 108 |  | 108.3077 | 11-Oct | 20 |  | 128
12-Oct | 98 |  | 98.4615 | 12-Oct | 30 |  | 128
13-Oct | 88 |  | 88.6154 | 13-Oct | 40 |  | 128
14-Oct | 78 |  | 78.7692 | 14-Oct | 50 |  | 128
15-Oct | 68 |  | 68.9231 | 15-Oct | 60 |  | 128
16-Oct | 58 |  | 59.0769 | 16-Oct | 70 |  | 128
17-Oct | 48 |  | 49.2308 | 17-Oct | 80 |  | 128
18-Oct | 38 |  | 39.3846 | 18-Oct | 90 |  | 128
19-Oct | 28 |  | 29.5385 | 19-Oct | 100 |  | 128
20-Oct | 18 |  | 19.6923 | 20-Oct | 110 |  | 128
21-Oct | 8 |  | 9.8462 | 21-Oct | 120 |  | 128
22-Oct | 0 |  | 0 | 22-Oct | 128 |  | 128